## SP posted on GFM Staff page
[6 empty] | Still needs to be determined |  | need to name point person
GFM Strategic Plan 2018-2022 4.1.19
# | Major Goals | # | Strategies | # | Key Actions/Projects | Desired Outcomes, Benchmarks | Time Frame (Years 1, 2,3,4,) | Person(s) Responsible
Initiative I: Plant exponentially and grow fruitful communities
1 | Plant witnessing communities on new campuses and new corners that, along with existing groups, long for revival as they shape whole-life disciples and seek the shalom of the campus (Sponsors: Kathy Cooper, Melodie Marske) | A | Deploy new staff (paid or Associate) and release selected current staff to plant new campuses/corners (see also Major Goal 4) | 1 | Each RD/RLT identifies/discerns campuses/corners, sets a four-year goal, and makes annual plans for planting (including itinerant and hub models where one CSM covers multiple campuses) | 90 new fellowships; 35 new campuses; 45 net gain in fellowships | per annual plans | Bobby + RDs
|  |  |  | 2 | Participate strategically in national planting programs: Area Accelerator (1.2); Every Corner Campus (3.1); Underserved geographies (2.2); Underserved Institutions (2.1) | TBD by program | most programs begin Yr 2 | Kathy C (Area Accel); Bobby (Every Corner); ______(under. geog); _______(under. instit)
|  |  |  | 3 | Each region motivates and releases staff to prayerfully explore and initially plant "adjacent" campuses per regional planting goals | Each region creates 4 or more bright spots around part-time planting | per annual plans | Kathy C
|  | B | Start missional prayer groups of faculty on every GFM-served campus and support undergrad staff catalyzing prayer groups | 1 | Use combo of vision casting, bright spot models, resources to spark staff to initiate/encourage prayer groups | Survey existing groups (Yr 1); start 25+ groups per year | track cummulative progress | Deb Clark + RDs
|  |  |  | 2 | Identify GFM staff to be available within the six pilot undergrad regions | TBD | 3 regions Yrs 1, 2; 3 regions Yrs 3,4 | Kathy Tuan + RDs
|  | C | Resource staff for training students/faculty for effective pursuit of our four core commitments: spiritual formation, community, evangelism/service integration | 1 | Resource GFM staff for excellence in training students/faculty in scripture engagement and faith/work integration | 1. Test Communcal Reading of Scripture | Scripture pilot Yr 1; | [prog. Coord.]
|  |  |  | 2 | Conduct survey/study of best models, structures, and practices for healthy/growing GFM chapters; utilize insights to resource campus staff |  | Yr 2
|  |  |  | 3 | Redesign, further develop, and integrate GFM virtual presence and communication platforms to serve ministry audiences (grads, faculty, emerging scholars), partners (donors, volunteers) and campus staff. | Hire and onboard new Communications Manager | Yr 1 | Lorrey + Nate
[6 empty] | Reposition ESN | Yr 1 | KTM + BG
|  |  |  | 4 | Develop resources and best practices for shaping students/faculty to engage with the Biblical call to "let justice roll down", esp. in our current historical context | TBD | TBD | Kathy C
|  | D | Innovate and press into best practices in witness/service to increase evangelistic fruit | 1 | Train staff, students, faculty, and volunteers to sponsor missional prayer groups of students and/or faculty, including prayer for revival (see also 1.B above) | 50% of grad chapters and 100% of faculty fellowships have groups by 2022 | Yr 2? | Melodie Marske
|  |  |  | 2 | Sponsor GFM One Plus Conversion Cohort 2.0 (and other programs as applicable) | TBD | Yr 1 & 2
|  |  |  | 3 | Strengthen the planning and implementation of robust NSO (and NFO) efforts that include evangelistic elements (i.e. invitations to cross thresholds of faith) | All CSMs annually write, execute, and report on NSO plans and efforts | Yr 2
# | Major Goals | # | Broad Strategies | # | Key Actions/Projects | Desired Outcomes/Benchmarks | Time Frame (Years 1, 2,3,4,) | Person(s) Responsible
Initiative II: Mobilize Partners to do ministry
2 | Identify, engage, and mobilize more campus staff and partners to advance the GFM mission (Sponsor: Don Paul Gross) | A | Recruit paid staff (and Associate staff) for current and new campuses; fill leadership, administrative and other non-campus roles | 1 | Each RD/RLT identifies priority campus staff positions to fill and makes annual plans for recruiting and hiring | _44__Paid Campus Staff Increase in Assoc. Staff | annually | Bobby, Marcia + SDs
|  |  |  | 2 | Each hiring director identifies positions to fill and makes annual plans for recruiting and hiring. | 10 Area Directors 9 Ministry Directors 4 Administrative roles | annually
|  |  |  | 3 | Increase staff recruitment and retention of people of color across GFM (see also 5.A below) | ____ new staff of color [# or %?]; $______raised for Diversity Fund | beg Yr 1 | BG, Marcia + RDs
|  |  |  | 4 | Facilitate learning community around effective recruiting strategies; set recruiting norms for SD/RLTs: 1. Every Undergrad RSC visited by GFM staff at least twice in four years 2. Every GFM SD communicates verbally with Undergrad counterparts twice per year (see 5.B.1) 3. Every SD includes recruiting plan in AMP. | 22 transfers from undergrad (included in A.1 total above) Qualitative: strong undergrad to GFM pipeline developed by Yr 4 | beg Yr 2 | [Point person]
|  | B | Recruitvolunteer partners (incl. students, faculty) to extend ministry to current and new campuses | 1 | Discover/incubate effective ways to find and work with an increasing number (and types) of volunteers helping staff on campus | Gain clarity on types of volunteers and deployment process; experiment Yr 2; TBD for Yr 3, 4 | beg Yr 2
|  |  |  | 2 | Consistently invite all students finishing their programs who plan to stay in the academy to be part of planting new campuses or corners (see C.3 above) | At least ____% of academy-bound grads followed up on new campus | beg Yr 1
|  |  |  | 3 | Discover/incubate ways to invite more faculty or administrators to partner in ministry to grad students on campus | TBD | Pilots beg Yr 2 | Deb Clark/KTM
|  |  |  | 4 | Discover/incubate strategies/structures to resource and coach volunteer partners serving students or faculty on campuses with no GFM staff | TBD | beg Yr 3
3 | Strengthen partnerships within InterVarsity, esp. with Undergrad Ministry (Sponsor: Bobby Gross) | A | Foster a culture of gracious initiative by all GFM staff to build strategic partnership with appropriate undergrad counterparts | 1 | GFMLT leads a change process (vision, bright spots, resources, incentives, accountability) that motivates GFM campus staff and SDs to annually undertake gracious initiative with Undergrad colleagues |  | beg Yr 1 (at Mundelein) | Bobby
|  |  |  | 2 | Orchestrate vision and expectations for GFM Staff Directors to annually engage their counterparts in three areas: relational connection, prayer, mutual support around key goals (esp. staff recruitment) | All SDs include in AMP steps to initiate (and grow) partnership with counterparts | Explore prarctices Yrs 1, 2; refine approaches for yrs 3,4 | ___________ + RDs
|  |  |  | 3 | initiate collegial practices at the shared campus level, focusing expectations and accountability around four core practices: prayer, NSO cooperation, resourcing grad school-bound seniors, and faculty connections | 80% of campus staff engaged in fruitful partnership on campus | beg Yr 1 ( at Mundelein) | Bobby + RDs
|  | B | Invest in the expansion of faculty ministry throughout InterVarsity by active support of the Faculty Ministry Leadership Team and its strategic plan | 1 | Support change process to reinforce vision and goals within GFM and across the wider field. | All GFM campus staff engaging faculty and calling them to the Faculty Four Loves | beg Yr 1 | Bobby
|  |  |  | 2 | Help Faculty Ministry create/curate best resources/practices for faculty ministry and platform accessbly for multiple audiences: faculty, GFM/Undergrad staff, and volunteers/partners | TBD | TBD | Kathy Tuan
|  |  |  | 3 | Support new faculty conferences/events (while sustaining four curren regional faculty conferences) | TBD | prob. Yr 3 or 4 | Deb Clark
|  |  |  | 4 | Work together to build robust faculty ministry data base | All GFM staff submit data for all appropriate faculty contacts | by Year 2 | Deb Clark
# | Major Goals | # | Broad Strategies | # | Key Actions/Projects | Desired Outcomes/Benchmarks | Time Frame (Years 1, 2,3,4,) | Person(s) Responsible
Initiative III: Become a thriving organization of thriving people
4 | Develop GFM staff as flourishing leaders on flourishing, inclusive teams through spiritual formation and organizational culture (Sponsors: Rob Howe, Lorrey Thabet, Marcia Wang) | A | Foster a culture of rest, joy, and generosity (model, teach, celebrate) | 1 | Encourage thoughtful sabbath keeping (per national emphasis Yr 1) and pattern of regular retreats | Most staff report healthy patterns | Keen attention to sabbath in Yr 1 | BG + GFMLT
|  |  |  | 2 | Model and celebrate generosity as the GFMLT with intention to see this spirit cascade to our teams and beyond | See Goal 3.B.2 re financial generosity; practice with time and hospitality as well | include in annual GFMLT plans | Bobby
|  | B | Grow teams of intercessors for staff, campuses and ministry teams | 1 | Resource staff for selecting and nurturing a core team of intercessors | Most staff have a core team of 4+ high-quality intercessors prahing weekly for them and the ministry | by Yr 2
|  |  |  | 2 | Build pattern of regualr missional prayer with colleagues | Most staff participate in missional prayer with colleagues (or partners) weekly; see also 5.A.1.2 and 5.B.1.1 | by Yr 2
|  | C | Encourage and equip all GFM teams to value each member’s uniqueness and sense of belonging | 1 | Call GFM to persistent prayer for grace and protection as we seek increasing diversity in our staff ranks, inclusive hospitality on all our teams, and growing effectiveness serving our diverse ministry audiences | TBD |  | Bobby & Marcia
|  |  |  | 2 | Provide cross-cultural educational opportunities for all GFM staff and Associate Staff working towards the 2030 vision | Choose a primary training opportunity/resource that we ask all GFM staff to take part in | TBD | Rob Howe
[6 empty] | Expect all GFM saff to include a development/learning goal in each Annual Ministry Plan | beg Yr 2 | Bobby + SDs
|  |  |  | 3 | Work with the Diversity Department: 1. Hiring Director of Diversity for GFM and welcoming leadership and help, 2. Utilize (new) organizational diversity scorecard to measure organizational diversity health | TBD | once director is named | Marcia Wang
|  | D | Invest in the longterm growth and flourishing of Black Scholars and Professionals (BSAP) | 1 | Appoint, welcome, and empower a new BSAP Director |  | Yr 1 on | Marcia Wang
|  |  |  | 2 | Work in partnership with the BSAP Director and leaders to develop vision and plans for the growth and impact of BSAP across GFM | TBD | Yr 1 on
5 | Partner to fully resource GFM staff through a multi-faceted, best practices approach to MPD (Sponsor: Lisa Liou) | A | Strengthen MPD by building sound rhythms and best practices into work by all staff raising funds | 1 | Develop shared MPD rhythms; enhance accountability around core practices of planning and the MPD Cycle (identifying, scheduling, and asking); provide for training of staff in light of skills assessments | All staff annually excute a solid MPD plan and see it as a normative part of their everyday work |  | RDs and SDs
|  |  |  | 2 | Provide excellent MPD training/coaching for newly appointed staff; offer ongoing training around best practices for all staff | GFM Participates in Fully Resourced MPD pilot offered nationally. | beg. Yr 1; Fully Resourced pilot Yr 1-2 | Lisa (for Pilot); Rob for all staff
|  |  |  | 3 | Equip and support all GFM Staff Directors (SDs) in raising strategic funds for their spheres | All GFM Staff Directors are successfully engaged in raising MPD+ gifts | underway Yr 1 | BG w GFMLT; Each member with his/her teams
|  |  |  | 4 | Provide updated training for all campus staff on how to lead a strong exit interview (participate in national GAPS program (5.1) as strategic and feasible) | All campus staff include in AMP. 80% of all graduating students participate in an exit interview. Chapter account(s) utilized at every campus. | GFM West in Pilot Yr 1, 2; extend to all GFM beg Spring 2019 | Lisa + ________
|  | B | Nurture communal mindsets and funding models (e.g. alumni, area, tethering, events, MPD+) | 1 | Inspire a mindset of abundance (vs. scarcity), a spirit of generosity (vs. self-protection), and a commitment to prayerful dependence on God (vs. anxiety) | Qualitative: increasing examples of generosity and sharing documented | beg Yr 1 | Bobby, Lisa, + GFMLT
|  |  |  | 2 | Encourage and sponsor experimentation in team models (practices and mentalities) of MPD; evaluate and identify effective practices (e.g. discover/incubate) | Qualitative: Team members view the MPD goal as an communal goal as well as individual goal. | GFMLT learning Yr 1; per region by Yr 3 | Lisa
Note on F29: Bobby Gross: (student leaders, faculty volunteers, undergrad staff, and volunteers from the community)
Note on G25: Bobby Gross: 30=50% incr. over transfers in previous four years